## Sheet1
Log Number | Team Member | Date | Hours | Minutes | Description |  | Hours | Minutes
1 | Aiden Patel, Andrew McFerrin, John Newman, Kai Achen, Landon Pyko | 2025-01-29 | 1 | 0 | discuss project idea and begin requirements stack | Aiden Patel | 16 | 12
2 | Aiden Patel, Andrew McFerrin, John Newman, Kai Achen, Landon Pyko | 2025-02-02 | 1 | 0 | finalize initial requirements stack | Andrew McFerrin | 6 | 27
3 | John Newman | 2025-02-06 | 0 | 30 | wrote two requirements artifacts | John Newman | 6 | 6
4 | Landon Pyko | 2025-02-05 | 0 | 15 | wrote one artifact. forgot to write this down yesterday | Kai Achen | 5 | 10
5 | Landon Pyko | 2025-02-06 | 0 | 20 | Looked into Hugging Face and CNN. Made the GitHub repository and shared it with group | Landon Pyko | 8 | 25
6 | John Newman | 2025-02-06 | 0 | 19 | wrote 2 requirements artifacts
7 | Aiden Patel | 2025-02-07 | 0 | 20 | organized documentation on GitHub. Started initial architecture document and then remembered we have a writer on the team that'll be better at that
8 | Aiden Patel | 2025-02-07 | 0 | 30 | did a little bit of research on models and put in some starter code to get an idea of what's going on | Total Time | 42 | 20
9 | Kai Achen | 2025-02-10 | 1 | 0 | completed DubBot training programs to learn more about how alt-text works and what makes effective and successful alt-text.
10 | Andrew McFerrin | 2025-02-10 | 0 | 30 | Looked into a couple image datasets and tried to generally understand whats even going on
11 | Landon Pyko | 2025-02-12 | 0 | 45 | Did some research and think that ResNet50 will be good for image classification. Imported some starter code for it. Also made a .gitignore to ignore the venv/ directory for if people want to use a virtual environment for dependencies
12 | Landon Pyko | 2025-02-12 | 0 | 30 | Spent a lot of time downloading dependencies and setting up venv. Created an instructions folder for everyone else for setting up the environment for it. Modified starter code to take in a image that I put in an image file. Properly classifies the image in output!
13 | Aiden Patel | 2025-02-12 | 0 | 40 | put in some starter code using DETR model that can generate multiple tags per image
14 | Kai Achen | 2025-02-12 | 0 | 35 | created compile_to_csv function that compiles images, tags, and flags into a csv file format for later use
15 | Aiden Patel, Andrew McFerrin | 2025-02-12 | 0 | 15 | discussed implementation of models
16 | Aiden Patel | 2025-02-12 | 1 | 0 | got some starter code in for entity recognition for text context and then burned a bunch of time messing with venv stuff because I don't have enough storage to download the GPU stuff for pytorch on my main drive
17 | Aiden Patel | 2025-02-13 | 1 | 30 | create tag_synthesizer that takes in tags and creates a caption and also created create_caption that takes in a photo and text to combine them and make a caption. Put some examples in and there's one in place on create_caption to test it (I know it's an illogical photo and text combo but that's the point)
18 | Landon Pyko | 2025-02-13 | 0 | 15 | Started on Sprint 2 Requirements Artifacts
19 | Aiden Patel | 2025-02-13 | 0 | 45 | set up environment on my desktop. made a requirements.txt to automatically install every package we need. proibably will need to update it. now trying to get the model to run on my gpu, not working so far but will report back
20 | Aiden Patel, Landon Pyko | 2025-02-13 | 0 | 5 | discuss running model on Nvidia cards
21 | Aiden Patel, Andrew McFerrin | 2025-02-13 | 0 | 12 | talk about models and realize we need another model for extracting text found on an image
22 | Landon Pyko | 2025-02-13 | 1 | 15 | Finally got it to work on my gpu.... frankly it took like twice as long as i said but i don't want to put that time in the log
23 | Aiden Patel, Landon Pyko | 2025-02-13 | 0 | 30 | talk through some code and about models being used
24 | Aiden Patel | 2025-02-14 | 0 | 45 | Rename files to be more descriptive and add caption model that helps create final output better
25 | Andrew McFerrin | 2025-02-14 | 1 | 15 | Familiarized myself with project, finished up rest of artifacts for sprint 2.
26 | Landon Pyko | 2025-02-14 | 1 | 0 | Fixed up tag generation by merging words together that started with ##. Weird thing that was happening but this fixed it. Also, did some other random stuff and made the sentence generator output grammatically correct sentences, even if it means they lose some of their meaning
27 | Aiden Patel | 2025-02-14 | 0 | 40 | Created a test script to batch test image and text combos
28 | John Newman | 2025-02-14 | 1 | 40 | Researched databases for training. Found one, attempted to trim dead links. Timeframe is on the scale of days. Not really feasible. Database is still usable, just program around using dead links
29 | John Newman | 2025-02-14 | 1 | 37 | Researched how to train models, spent time prompt engineering, banged my head against a wall, discussed and thought about how model will work and train
30 | Kai Achen | 2025-02-15 | 0 | 20 | tinkered with torch cuda sentence generator prompt using some verbiage from the section508.gov site on what makes appropriate alt-text
31 | Kai Achen | 2025-02-15 | 0 | 20 | created flow chart artifact for what type of alt-text should be generated based on image attributes and website context
32 | Landon Pyko | 2025-02-15 | 0 | 30 | Did some comments
33 | Aiden Patel | 2025-02-16 | 1 | 10 | Added URL image functionality and created 'main' facing method for captioner to connect with scraper in the future
34 | Aiden Patel | 2025-02-16 | 0 | 20 | create worklog
35 | Aiden Patel | 2025-02-16 | 0 | 5 | cleaned up sprint 2 artifacts and submitted it as well as the requirements stack
36 | Aiden Patel | 2025-02-21 | 0 | 5 | fork sprint 1 repo for second sprint and invited the team for collaboration
37 | Aiden Patel | 2025-02-21 | 1 | 10 | Created web scraper and connected it to the captioner in the main_captioner.py file. Ran the test on the lied center site so the output can be seen at lied_center.csv
38 | Aiden Patel | 2025-02-21 | 0 | 23 | create quick script to convert csv output to pdf to show caption next to image
39 | Aiden Patel | 2025-02-21 | 0 | 8 | add pdf creator to test script
40 | Kai Achen | 2025-02-24 | 0 | 20 | learn Aiden's new changes and write some basic information in the README on how to use the project in its current state
41 | Kai Achen | 2025-02-24 | 0 | 30 | fix some import statements and attempted to make web scraper also access images in "revolution slider" (lied specific wordpress plugin) but not working correctly yet
42 | Kai Achen | 2025-02-24 | 0 | 5 | added timer to main_captioner.py
43 | Andrew McFerrin | 2025-02-24 | 0 | 15 | reviewed sprint requirements and understood the scraper code
44 | Landon Pyko | 2025-02-24 | 1 | 0 | tried tinkering with some model generation inputs but didn't make much progress, will look at it again tomorrow
45 | Aiden Patel | 2025-02-24 | 0 | 20 | pushed potentially broken code because I wanted to have it saved in case of a crash. Created test function to test multiple sites so I'm going to run that now to get timings
46 | Aiden Patel | 2025-02-24 | 0 | 20 | thought something was broken with the code so i was crashing out but realized i forgot the 'u' at the end of 'edu' in a url and that's why it was breaking
47 | Aiden Patel | 2025-02-24 | 0 | 30 | added bypass for images that have failures processing or process nothing
48 | Aiden Patel | 2025-02-24 | 0 | 5 | added another thing to handle poor response code from loading an image
49 | Aiden Patel | 2025-02-24 | 0 | 10 | handle poor response code from loading image in PDF creator
50 | Aiden Patel | 2025-02-24 | 0 | 3 | more try except blocks added to catch errors in image loading
51 | Andrew McFerrin | 2025-02-24 | 2 | 0 | Worked on new branch "front_end" to reorganize structure of project to facilitate flask. Created basic flask website with initial necessary elements. Reran main_captioner to ensure it still works with restructured project
52 | Aiden Patel | 2025-02-25 | 0 | 10 | added another dead link check and reviewed test results
53 | Aiden Patel | 2025-02-25 | 0 | 36 | Ran tests and put in some starter code for multiprocessing that is currently blocked from running
54 | Aiden Patel | 2025-02-25 | 1 | 15 | update multiprocessing to be functional without ruining single process option. Ran test on lied center and found 210 second decrease in run time when using 4 processes over 1
55 | Aiden Patel | 2025-02-25 | 0 | 10 | update worklog
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100